## Delivery Plan
Item Code Studio — Delivery Plan
Prepared for Anuraag · 6 August 2026 · v2.0 · R1-R5 are today's build runs. S0 = already built and verified. NEEDS INPUT = cannot be done by me; the Notes column says what is required.
ID | Epic | Story | Acceptance criteria | Priority | Points | Run | Status | Depends on | Notes
K1 | E0 Brand & Shell | Apply the MiniMines theme | Palette from m-mines.com (#001b2e navy, #04aed1 teal, #3b6e93 steel), Barlow typeface, minimines-logo.svg in the header. Light and dark both legible. | Must | 5 | R1 | Not started |  | Reused from ATT_Platform, not reinvented
K2 | E0 Brand & Shell | Remove the stats block | The counts panel in the bottom-left corner is gone. Nothing shifts or leaves a gap. | Must | 1 | R1 | Not started | K1 | Your instruction
A1 | E1 Access & Identity | Split landing page | One page, two halves: Decoder left, Directory right, Log in top-right. No credentials needed to use either half. | Must | 8 | R1 | Not started | K1 | The main page for everyone
A2 | E1 Access & Identity | Decoder half | Paste any code, get head, sub-head, group, every spec with its per-group label, vendor. 00 reads 'not applicable'. Malformed input explains why. | Must | 3 | R1 | Not started | A1
A4 | E1 Access & Identity | Directory half | Search 1,947 items by code, name or description. Row opens a read-only detail card. | Must | 5 | R1 | Not started | A1
A3 | E1 Access & Identity | Dictionary browse | Search 889 groups; open one to see its spec slots and values. Reachable from the directory half. | Must | 3 | R1 | Not started | A4
A8 | E1 Access & Identity | Server-side write protection | Every mutating endpoint returns 401 to an unauthenticated caller invoked directly, not merely hidden in the interface. | Must | 3 | R1 | Not started |  | The actual boundary
A5 | E1 Access & Identity | Login | Username and password against the user table, scrypt hashed. Bad credentials give one generic message. | Must | 5 | R2 | Not started | A8 | Simple by instruction
A6 | E1 Access & Identity | Session handling | HMAC-signed HttpOnly cookie, 12h expiry, logout clears it. Expiry returns to the landing page, never a blank screen. | Must | 3 | R2 | Not started | A5
A9 | E1 Access & Identity | Attribution from session | created_by comes from the session. The forgeable X-User header is deleted from the codebase. | Must | 2 | R2 | Not started | A6 | Closes a real hole
A7 | E1 Access & Identity | Creator shell | After login: Create, Item master, Activity. The landing page stays reachable while logged in. | Must | 3 | R2 | Not started | A6
A10 | E1 Access & Identity | User management | manage.py adduser / disable / resetpw. At least one active creator must always remain. | Must | 3 | R2 | Not started | A5 | CLI is enough at this size
A11 | E1 Access & Identity | Change own password | A logged-in creator can change their password; the old one is required. | Should | 2 | R2 | Not started | A5
C10 | E3 Code Engine | Create screen with the three phases | Paste or upload, then every line shows what phase 1 found, which group phase 2 chose, and what phase 3 read into each slot. | Must | 5 | R3 | Not started | A7 | Engine exists; this is the gated screen
F8 | E5 Invoice & OCR | Invoice upload wired into Create | Drop a PDF, scan, photo, Excel or CSV and get one row per line item, each resolving independently. | Must | 5 | R3 | Not started | C10 | Engine exists
K3 | E6 Master & Restructure | Conditional cascading dropdowns | Choosing a head filters sub-heads to that head. Choosing a sub-head filters groups to that sub-head only. Choosing a group re-renders its spec slots with that group's labels. | Must | 8 | R3 | Not started | C10 | Core of your edit requirement
K4 | E6 Master & Restructure | Live code recomputation | Any change to head, sub-head, group, spec or vendor recomputes the code immediately, obeying the interior-00 and trailing-truncate rules. | Must | 5 | R3 | Not started | K3
K11 | E3 Code Engine | Item-level number reservation | Moving an item to another group frees its old position under that head and sub-head into the vacancy ledger. New arrivals take a fresh number; the reserved one is released only to a later item with the same spec tuple, and dropped when the sub-head is revoked. | Must | 8 | R3 | Not started | K4 | The logic you said was missing
K12 | E6 Master & Restructure | Vacancy visibility | Reserved numbers at both group and item level are listed with what freed them and what would claim them. | Should | 3 | R4 | Not started | K11
K5 | E6 Master & Restructure | Edit before submit | Every proposed code carries an Edit control. Nothing is written until Submit. | Must | 3 | R3 | Not started | K4
B5 | E2 API v1 | Idempotent commit | A commit carries a client token; replaying it returns the original code instead of issuing a second. | Must | 3 | R3 | Not started | K5 | Guards double-click
C8 | E3 Code Engine | Concurrent issuance safety | Two creators submitting in the same second cannot receive the same code. Proven by a concurrent test, not by argument. | Must | 5 | R5 | Not started | B5
K6 | E6 Master & Restructure | Item master as an editable directory | Same rows and columns as the public directory, every field editable in place, with the same cascading dropdowns. | Must | 8 | R4 | Not started | K3 | Your instruction
K7 | E6 Master & Restructure | Revision history | Every save snapshots the whole row with who, when and what changed. Nothing is overwritten in place. | Must | 8 | R4 | Not started | K6 | The version-control requirement
K8 | E6 Master & Restructure | Revert to a previous version | Any earlier version can be restored in one click. The revert is itself a new version, so it can be undone too. | Must | 5 | R4 | Not started | K7
K9 | E6 Master & Restructure | Activity feed with diffs | Activity shows field-level before and after, filterable by person, item and date, with Revert on each entry. | Must | 5 | R4 | Not started | K7
G3 | E6 Master & Restructure | Move, merge, retire, rename | Each shows a full impact preview listing what re-codes and what stays frozen. | Must | 8 | S0 | Done |  | Built and tested on group Tissue
K10 | E6 Master & Restructure | Revert respects frozen codes | A revert never rewrites a code that is live in ERPNext. It restores fields and says plainly what it could not restore. | Must | 5 | R4 | Not started | K8 | Where version control meets freeze-on-first-use
G5 | E6 Master & Restructure | Excel export | Item_Master, Item_Code_Master, Code_Mapping and Audit_Trail in one workbook. | Must | 5 | S0 | Done
B1 | E2 API v1 | Version and freeze the contract | Everything served under /api/v1 exactly as the PDR documents it. | Must | 5 | R5 | Not started | A8 | So the larger system can build against it
B2 | E2 API v1 | Uniform error envelope | Every failure returns ok:false with a stable machine code. No stack traces reach the client. | Must | 3 | R5 | Not started | B1
B3 | E2 API v1 | Self-served API docs | GET /api/docs lists every endpoint with request and response examples. | Should | 3 | R5 | Not started | B1
B4 | E2 API v1 | Pagination and filtering | List endpoints take q, limit, offset, status and return total alongside rows. | Should | 2 | R5 | Not started | B1
B6 | E2 API v1 | Public endpoint hardening | Payload caps and a simple per-IP rate limit on public reads. | Should | 2 | R5 | Not started | A8
B7 | E2 API v1 | Smoke suite | A stdlib script exercises every endpoint including auth failures and runs in under a minute. | Must | 5 | R5 | Not started | B2
J7 | E9 Deploy & Handover | Deploy to the internal server | Runs on the nominated machine, reachable by hostname on the LAN, starts on boot, survives a restart. | Must | 5 | R5 | Not started | B7 | Internal grade, not production grade
J2 | E9 Deploy & Handover | Automated backup | Daily copy of itemcode.db plus a weekly Excel export, both written off the host machine. | Must | 3 | R5 | Not started | J7
J8 | E9 Deploy & Handover | Seed and go-live check | Fresh seed from the source workbooks on the server; counts match; a code is issued end to end. | Must | 3 | R5 | Not started | J7
C1 | E3 Code Engine | Code grammar assembly | Interior gap 00, trailing gaps dropped, vendor forces 17. Only 7/9/11/13/15/17 accepted. | Must | 8 | S0 | Done |  | Verified against RMBS0010206100007
C2 | E3 Code Engine | Three-phase resolver | Phase 1 stops on an existing code; phase 2 resolves head/sub-head/group; phase 3 resolves specs and vendor. | Must | 13 | S0 | Done | C1
C3 | E3 Code Engine | Prefix collision ladder | A taken 4-letter prefix walks to the next free combination, checked against groups and live ERP codes. | Must | 3 | S0 | Done | C1 | CEEU preserved as seeded
C4 | E3 Code Engine | Per-sub-head numbering and vacancies | Numbers restart per sub-head. A moved group's number is parked, released only to a >=88% name match. | Must | 5 | S0 | Done | C1 | Your rule
C5 | E3 Code Engine | Freeze on first use | A code live in ERPNext is never rewritten by a structural change; it is kept and flagged stale. | Must | 5 | S0 | Done | C4 | Needs your confirmation
C6 | E3 Code Engine | Decoder with per-group labels | Decode reports each slot's meaning for that group, and 00 as not applicable. | Must | 3 | S0 | Done | C1
C7 | E3 Code Engine | Ambiguous spec is a question | A declared slot with no determinable value blocks submission; it is never auto-numbered. | Must | 3 | S0 | Done | C2 | Caught a real collision
D1 | E4 Matching & LLM | Deterministic normaliser | Units, casing, punctuation, synonyms and noise words folded before scoring. | Must | 5 | S0 | Done
D2 | E4 Matching & LLM | Blended fuzzy scorer | 0.45 token-set + 0.30 token-sort + 0.25 soft-Jaccard. | Must | 5 | S0 | Done | D1 | Single-metric gave a false 100%
D3 | E4 Matching & LLM | Alias learning | An override is stored as an alias so the same wording resolves next time without an LLM call. | Must | 3 | S0 | Done | D1
D4 | E4 Matching & LLM | LLM provider abstraction | One config line switches anthropic / gemini / openai / ollama / none. | Must | 5 | S0 | Done |  | Scaffold complete
D9 | E4 Matching & LLM | Invert to LLM-first matching | The LLM decides group then specs on every judgement call; the rules produce the shortlist and constraints and hold the veto. Every decision stamped matched_by. | Must | 8 | R3 | Not started | D4 | Your instruction - reverses the earlier design
D10 | E4 Matching & LLM | Fallback on rate limit or quota | 429, timeout, bad key or no network falls straight through to the deterministic result, marked matched_by:rules. The tool never stops working. | Must | 5 | R3 | Not started | D9 | The always-there fallback
D11 | E4 Matching & LLM | Cache and batch LLM calls | Results cached on normalised text; a 20-line invoice resolves in one call, not twenty. Exact phase-1 hits never call out. | Must | 5 | R4 | Not started | D9 | Keeps LLM-first affordable
D7 | E4 Matching & LLM | LLM guardrails | The model may only pick from the shortlist or answer none. It can never mint a code. | Must | 3 | S0 | Done | D4
D8 | E4 Matching & LLM | Graceful degradation | Provider down or key invalid falls back to fuzzy plus a human question, never a crash. | Must | 2 | R5 | Not started | D4
F1 | E5 Invoice & OCR | Multi-format extraction | Text, PDF, scanned PDF, image, Excel and CSV all produce a line list. | Must | 8 | S0 | Done
F2 | E5 Invoice & OCR | Extraction cascade | Tables, then text layer, then OCR per page. Only pages without text go to OCR. | Must | 5 | S0 | Done | F1
F6 | E5 Invoice & OCR | Field extraction | Description, quantity, UoM, rate, HSN and line-level vendor. Header supplier ignored. | Must | 5 | S0 | Done | F1 | Your rule: line vendor only
F7 | E5 Invoice & OCR | Independent batch handling | A 20-line invoice yields 20 proposals; one failure never blocks the rest. | Must | 3 | S0 | Done | F1
G1 | E6 Master & Restructure | Item master screen | Search, filter and edit, attributed and logged. | Must | 5 | S0 | Done
G2 | E6 Master & Restructure | Field edits never touch the code | Enforced in the API, not only the interface. | Must | 2 | S0 | Done | G1
G4 | E6 Master & Restructure | Code mapping ledger | Every old-to-new pair recorded and exported. | Must | 3 | S0 | Done | G3
H1 | E7 ERPNext | REST client | Login, retry and error surfacing against UAT and PROD. | Must | 3 | S0 | Done
H2 | E7 ERPNext | Pull live item list | One click refreshes the reserved-code set from live ERPNext. | Must | 3 | S0 | Done | H1
H3 | E7 ERPNext | Dry-run payload preview | Shows the exact JSON that would be posted, writes nothing. | Must | 3 | S0 | Done | H1
D5 | E4 Matching & LLM | Choose the LLM provider and wire the key | A provider is chosen, the key stored outside the repo, per-call cost logged. | Must | 3 | NEEDS INPUT | Blocked | D4 | Needs: an API key
D6 | E4 Matching & LLM | Calibrate the 60% threshold | 200 real invoice lines run; false accepts and false asks measured; the chosen number recorded. | Must | 8 | NEEDS INPUT | Blocked | D5 | Needs: 200 real lines + a key
F3 | E5 Invoice & OCR | Install Tesseract on the host | OCR verified working on the machine that will host the app. | Must | 2 | NEEDS INPUT | Blocked | J7 | Needs: admin rights on the host
F4 | E5 Invoice & OCR | OCR accuracy on real invoices | Ten real scanned invoices processed; per-field accuracy recorded; failures listed. | Must | 5 | NEEDS INPUT | Blocked | F3 | Needs: 10 real scanned invoices
F5 | E5 Invoice & OCR | Line filter tuning | GST rows, totals, bank details and signatures excluded on the real sample. | Must | 3 | NEEDS INPUT | Blocked | F4 | Needs: the same invoices
H9 | E7 ERPNext | Service account and role | A dedicated itemcode.studio user with an Item Code Studio role, API key not password, delete refused everywhere, transactions and permission doctypes refused. | Must | 5 | NEEDS INPUT | Blocked |  | Needs: someone with ERP admin rights
H10 | E7 ERPNext | Prove the guardrail | The service account attempts one write to Stock Entry and one to Custom Field. Both must fail with 403. | Must | 3 | NEEDS INPUT | Blocked | H9 | A guardrail nobody has tried is not a guardrail
H11 | E7 ERPNext | Sub-head to Item Group mapping | Each of our 46 sub-heads maps to one of ERPNext 23 item groups. Mapping is data, not code, and is editable. | Must | 5 | R5 | Not started |  | ERP has 23 groups, we have 889
H12 | E7 ERPNext | Validate UoM and HSN against ERP | Stock UoM checked against the 240 UOM records and HSN against the 18,689 GST HSN Code records before any write. | Must | 3 | R5 | Not started | H11 | Stops bad values at source
H13 | E7 ERPNext | Populate the ERP specification fields | item_specification_1-4 and item_vendor written on create so the decode lives in ERPNext too. | Should | 5 | NEEDS INPUT | Blocked | H4 | Needs: decision on Wahni parallel framework
H4 | E7 ERPNext | Live create on UAT | Submitting creates the Item in UAT with our code as item_code. | Must | 5 | NEEDS INPUT | Blocked | H3 | Needs: your go-ahead to write
H5 | E7 ERPNext | Per-creator ERP credentials | Each creator authenticates to ERPNext as themselves. | Must | 5 | NEEDS INPUT | Blocked | A5 | Needs: ERP logins per person
H6 | E7 ERPNext | Rename cascade | When an unfrozen item re-codes, the ERPNext rename is issued and confirmed. | Must | 5 | NEEDS INPUT | Blocked | H4 | Needs: UAT writes first
H7 | E7 ERPNext | Drift reconciliation report | Lists app-only, ERP-only and disagreeing fields. | Should | 5 | NEEDS INPUT | Blocked | H2 | Needs: UAT writes first
H8 | E7 ERPNext | PROD go-live | Writes enabled on PROD after a clean UAT week. Rollback path written down. | Must | 3 | NEEDS INPUT | Blocked | H4;H5 | Needs: your sign-off
I1 | E8 Data Quality | Resolve 10 unmatched items | The 10 seeded items with no matching group are assigned or corrected. | Must | 2 | NEEDS INPUT | Blocked |  | Needs: 10 judgement calls from you
I2 | E8 Data Quality | Triage 175 junk ERP codes | LCO-1, IBC TANKS, Iron and bare numbers each disabled or re-coded. | Should | 5 | NEEDS INPUT | Blocked | H4 | Needs: ERP write access
I3 | E8 Data Quality | Policy for 614 non-grammar codes | Leave frozen, or plan a one-time re-code. Written either way. | Must | 3 | NEEDS INPUT | Blocked |  | Needs: a business decision
I4 | E8 Data Quality | Group de-duplication campaign | 889 groups reviewed, duplicates merged, an agreed target reached. | Must | 13 | NEEDS INPUT | Blocked | G3 | Needs: your judgement on 889 groups
I5 | E8 Data Quality | Spec value de-duplication | Within-group duplicate values merged, aliases preserved. | Should | 5 | NEEDS INPUT | Blocked | I4 | Needs: I4 first
I6 | E8 Data Quality | HSN backfill | Blank and 4-digit HSN filled where a correct 8-digit code exists. | Should | 5 | NEEDS INPUT | Blocked |  | Needs: CA verification
J1 | E9 Deploy & Handover | Nominate the host machine | An always-on machine, sleep disabled, fixed hostname. | Must | 2 | NEEDS INPUT | Blocked |  | Needs: which machine
J4 | E9 Deploy & Handover | Operator SOP and training | One-page sheet plus a session with the creators. | Must | 3 | NEEDS INPUT | Blocked | J7 | Text drafted in PDR §8
J5 | E9 Deploy & Handover | Support runbook | Restart, restore, add a user, rotate a key, who to call. | Must | 3 | NEEDS INPUT | Blocked | J2
J6 | E9 Deploy & Handover | Two-week post-launch watch | Daily check of codes issued, questions raised and mismatches, with a written close-out. | Must | 5 | NEEDS INPUT | Blocked | H8 | Needs: two weeks to pass
G6 | E6 Master & Restructure | Bulk operations | Select many items and move or edit them in one previewed action. | Could | 5 | BACKLOG | Not started | G3 | Deferred, not needed for go-live
C9 | E3 Code Engine | Vacancy claim override | An admin can release or reassign a parked number, with a reason recorded. | Could | 3 | BACKLOG | Not started | C4 | Deferred
TOTAL

## Runs
Build runs — one sitting, today
Points roll up from the Delivery Plan. Each run ends with something you can open and use.
Run | What it delivers | Points | Stories | Done | Complete %
S0 | Already built: the grammar, all three phases, matching, invoice extraction, the master, restructuring, export, ERP read
R1 | MiniMines theme and logo, the split landing page — decoder one side, directory the other, log in on top. Stats block removed
R2 | Login, sessions, attribution from the session, user management, the creator shell behind the gate
R3 | The create screen: paste or upload an invoice, three phases shown per line, cascading head-sub-head-group dropdowns, live code recomputation, edit before submit
R4 | Item master as a fully editable directory, revision history on every save, one-click revert, activity feed with field-level diffs
R5 | API frozen at /api/v1 with a real error contract, smoke suite, deployed to the internal server, starts on boot, daily backup
NEEDS INPUT | Blocked on something only you or the organisation can supply — see the next tab
BACKLOG | Agreed but not needed for go-live
TOTAL
Buildable today (R1-R5):
Blocked on your input:
Every run leaves the app working. If we stop after R3 you still have a usable tool, just without version control.

## Needs Your Input
What I cannot do for you
These are real work items, not excuses. Each needs a thing only you or the organisation can supply. Give me the input and the work moves in the same sitting.
What I need from you | Unblocks | Points | Why it cannot be faked
An LLM API key (Gemini Flash is free at this volume) | D5, D6 — the sub-60% matching layer | 11 | Without a provider the third matching layer never runs. Fuzzy alone still works, but the hard lines stay questions for the operator.
Ten real scanned or photographed invoices | F3, F4, F5 — OCR proven end to end | 10 | OCR accuracy depends entirely on your paper: fonts, stamps, skew, scan quality. Any number I quote from synthetic files would be fiction.
Written go-ahead to write into ERPNext UAT | H4, H6, H7 — items actually created | 15 | Writing to a live system is your call, not mine. Dry-run shows the exact payload first.
An ERPNext login per creator | H5, H8 — PROD go-live | 8 | A shared account leaves an audit trail naming nobody. This blocks PROD by design, not by preference.
Which desktop or box hosts it, and can it stay on | J1, F3, J7 — deployment | 9 | Everything else is ready. I need a machine name and admin rights on it.
Your judgement on 889 groups: how far to cut | I1, I3, I4, I5 — the clean-up | 23 | Which groups are genuinely duplicates is a business judgement about your materials. Guessing would corrupt the master.
CA verification of specialised HSN codes | I6 — HSN backfill | 5 | Carried over from the item master work. Wrong HSN is a GST exposure, so it needs a human who is accountable.
Two weeks after go-live, and the creators' time | J4, J5, J6 — training and the watch | 11 | Training needs people in a room. The watch needs time to pass.
TOTAL BLOCKED

## Epics
Epics
Calculated from the Delivery Plan.
Epic | What it covers | Stories | Points | Done pts | Complete %
E0 Brand & Shell | MiniMines palette, logo and typeface; the stats block removed
E1 Access & Identity | The split landing page anyone can use, and a login that leads to creation
E2 API v1 | A stable, documented, versioned contract for the larger system
E3 Code Engine | The grammar, three phases, numbering, vacancies, freeze-on-first-use
E4 Matching & LLM | Normaliser, fuzzy blend, alias learning, LLM below 60% confidence
E5 Invoice & OCR | Reading text, PDF, scanned and photographed invoices into resolvable lines
E6 Master & Restructure | Editable master, cascading dropdowns, revision history, revert, restructuring
E7 ERPNext | Reading live truth, and writing items back on submit
E8 Data Quality | Duplicate groups, junk codes, missing HSN
E9 Deploy & Handover | Server, backup, start-on-boot, training, runbook, post-launch watch
TOTAL

## Risks
Risks
# | Risk | Impact | Likelihood | Response | Status
1 | Building all five runs in one sitting means less testing per feature than the six-sprint plan allowed. | High | Certain | Each run ends working and is exercised against the real seeded data before the next starts. Where a run is thin, it is named in the handover rather than hidden. | Accepted
2 | Version control plus freeze-on-first-use interact awkwardly: a revert cannot restore a code that ERPNext has frozen. | High | Likely | K10 makes revert restore fields only, and say plainly what it could not restore. Never a silent partial revert. | Open
3 | OCR accuracy is completely unmeasured on your paper. | High | Possible | Blocked on ten real invoices. Until then OCR is present but unproven, and the handover says so. | Blocked
4 | The host is a single point of failure. If it sleeps, nobody can issue a code. | High | Likely | Daily off-machine backup, start-on-boot. Move to an always-on box if it bites. | Open
5 | Passwords cross the LAN in the clear over plain HTTP. | Medium | Certain | Accepted for an internal tool. Use passwords not reused elsewhere. TLS if it ever leaves the LAN. | Accepted
6 | Group de-duplication keeps slipping. Every month more codes freeze and the clean-up gets permanently dearer. | High | Likely | Blocked on your judgement. This is the item I would push hardest to unblock first. | Blocked
7 | Writing to PROD under a shared account leaves an audit trail naming nobody. | High | Certain | Per-creator ERP credentials block PROD go-live by design. | Blocked
8 | Anyone who can log in can restructure the master, with no approval gate, by instruction. | Medium | Possible | Preview, attribution, full revision history and one-click revert. Revisit only if it actually causes harm. | Accepted
9 | A structural change re-codes an item ERPNext has already transacted. | High | Unlikely | Freeze-on-first-use makes it impossible by design; every change is previewed first. | Mitigated
10 | The larger system builds against an API that then shifts underneath it. | Medium | Possible | R5 freezes the contract at /api/v1 before anyone integrates. | Open

## Decisions
Decision log
Amber rows need your word before or during the build.
# | Decision | Rationale | Status
1 | Variable-length codes, never padded | Interior gaps carry meaning as 00; trailing gaps carry none. Lengths 7/9/11/13/15/17. | Locked
2 | Vendor sits last, only in groups that declare it | Four battery groups declare a Maker slot. Elsewhere one item keeps one code regardless of supplier. | Locked
3 | Vendor from the invoice line only, never the header | A supplier named at the top of a page says nothing about an individual line. | Locked
4 | No -R / -W / -F state suffixes | Removed entirely. | Locked
5 | Spec slot meaning is per group | Air Freshener uses Type and Size; Battery Pack uses Form Factor, Chemistry, Size, Capacity, Maker. | Locked
6 | Group numbers restart inside each sub-head | 999 per sub-head is ample at 889 groups. | Locked
7 | A vacated group number is parked, not reused | Released only to a >=88% name match. The number carries the meaning of what held it. | Locked
8 | Prefix collisions walk to the next free combination | Seeded prefixes read from codes already issued, so CEEU and its like survive. | Locked
9 | No approval workflow | Preview, attribution, revision history and revert replace permission. | Locked
10 | Two tiers, not roles: public read, login to create | You have two kinds of people and one permission. A role matrix would never earn its keep. | Locked
11 | Landing page is split: decoder one side, directory the other | Most people only ever need to look something up. That is the front door. | Locked
12 | Item master is the editable twin of the public directory | Same rows, same columns, editable behind the login. | Locked
13 | Every save is a version, and any version can be restored | Replaces approval with reversibility. | Locked
14 | Simple username and password, no OTP, no SSO | Read from 'simple authentication'. If you meant a one-time code by email or SMS, say so — it needs a delivery channel and is a different build. | For confirmation
15 | LLM-first matching, rules as guardrail and fallback | The LLM decides group then specs; the rules build the shortlist, hold the veto, and take over entirely on rate limit or outage. | Locked
19 | Vacated numbers are claimed by matching, not by queue position | A reserved number waits for something that genuinely matches what left, rather than going to the next arrival. | For confirmation
20 | Populate Wahni's ERPNext specification fields | ERP already has item_specification_1-4, item_vendor and 62 spec records, barely used. Populate them rather than leave two parallel systems. | For confirmation
21 | Map our taxonomy onto ERP Item Groups at sub-head level | ERP has 23 item groups, we have 889. Creating 889 would wreck their reporting tree. | For confirmation
16 | Freeze on first use: codes live in ERPNext are never rewritten | Submitted Frappe documents are immutable and renames cascade. Kept and flagged stale instead. | For confirmation
17 | A revert restores fields, never a frozen code | Where version control meets ERPNext reality. It says plainly what it could not restore. | For confirmation
18 | One SQLite file on one internal server | Makes duplicate codes structurally impossible. Accepts the host as a single point of failure. | Locked

## Definition of Done
Definition of Done
Compressed to one sitting, so this is the floor, not the ceiling.
1 | The acceptance criteria on the Delivery Plan row are met as written, not as reinterpreted.
2 | Exercised against the real seeded data — 889 groups, 1,947 items, 2,677 live ERP codes — never a toy fixture.
3 | Any rule that protects the master is enforced in the API, not only in the interface.
4 | One failure path tried on purpose, producing a clear message rather than a crash or a silent wrong answer.
5 | Every write is attributed to the authenticated user and appears in the activity log.
6 | The app still starts and the previous runs still work.
7 | Anything thin or untested is written into the handover, not carried in someone's head.